Town of Schroeppel

69 County Route 57A,

Phoenix, NY 13135

Phone 695-6231 / Fax 695-1210

Supervisor

Joann Nazarian

Council Members:								                Town Clerk:

Joann Nazarian 								         Darlene Owens

Zachary Gelling 							   Highway Superintendent:

Matt Notaro								         		      Jeff Jones

Tom Millert								    	    Receiver of Taxes:

Justin Hart								                                  Ryan Wood

October 28, 2024

Below is the TENTATIVE schedule for the Bankrupt Road Water District.

- Schedule for next 30 days

  - Bill Langdon Highlander PM went over schedule.

  - 10/14 Highlander will remobilize/drill schedule

  - 10/21 Highlander can start drilling

  - 11/21 Drilling complete. Estimating a month given good weather and no issues drilling

  - 12/15 Complete service installations – couple weeks after drilling; should be able to test concurrently

  - 12/30 Possible for residents to connect by the end of the year; Joann receiving multiple calls and would like to have a clear deadline.

  - Success is dependent on weather/temperature

  - Shutdown for winter contingent on weather and temperature.

If you have any additional questions, please feel free to call our office.